## Home
SAM QI Project Log
The Society for Acute Medicine (SAM) quality improvement (QI) log for one project. Keep one shared file for the whole project on the team drive or in Teams, so that everyone edits the same copy. Do not email copies around.
PROJECT
Project title | Enter…
SMART aim | To increase/reduce [measure] from [X] to [Y] by [date]: specific, measurable, achievable, relevant and time-bound…
WHO quality domain targeted | World Health Organization (WHO) domain: pick from dropdown →
Ward / setting | Enter…
Project lead | Enter…
Consultant supervisor | Enter…
Team members | Enter…
Key stakeholders: who must say yes? | Ward manager, pharmacy, information technology (IT)… name them before you launch
Audit registration no. and date | Register BEFORE baseline, then enter no. here
Project type | Pick from dropdown →
Project start date | Enter…
Intervention start date | Enter…
Current step | Pick from dropdown →
PITCH AND CHANGE (Steps 2 to 3) | Draft it on the Pitch and 2×2 tabs at aimqa.github.io/Test-/diagram-tool.html, then paste the final wording here.
1 The problem | What’s going wrong, and for which patients, as you’ve seen it on the ward…
2 The number | One honest local figure: “12 of 20 charts last week”…
3 The aim | From [X] to [Y] by [date], the same as the SMART aim above…
4 Why it matters | The WHO quality domain it targets, and what it means for patients…
5 The ask | A named supervisor, and a “yes, go ahead” to collect baseline data…
Root cause (from 5 Whys) | The system cause you stopped at, such as a process, a form or a step (never a person)…
Change idea for cycle 1 | Your quick win: high impact and low effort, top left of the 2×2…
AT A GLANCE (updates itself)
0 of 5 steps done
0 open actions
1 data point on the run chart
0 of 18 SQUIRE items covered
Draw your process map and driver diagram → aimqa.github.io/Test-/diagram-tool.html
SAM QI Diagram Tool: WHO quality lens built in · worked example on venous thromboembolism (VTE) · export the PNG straight into your slides
HOW TO USE THIS PROJECT LOG
– White bordered cells and grey ‘Enter…’ text are yours to overwrite.
– Grey italic EXAMPLE rows show the expected format. Overwrite or delete them.
– Cells with a dropdown show an arrow when clicked. Pick from the list.
– One tab per job, in step order: Steps: where the project is · Actions Log: who’s doing what · Process Map: what actually happens (Step 1) · Causes: why it happens (Step 1) · Data Plan: the 3 measures (Step 2) · Data Log: the run chart (Step 4) · Diary: what people said and what changed (Step 4) · PDSA Log: one row per Plan–Do–Study–Act (PDSA) cycle (Step 4) · SQUIRE Check: the 18 items of SQUIRE (Standards for Quality Improvement Reporting Excellence), before you present (Step 5) · Share and Replicate: hand it on to another ward or trust (Step 5).
– New to the team? Read the SAM QI Roadmap deck first. This log follows the 5 steps, and its tabs run in step order.
– Draw the diagrams in the tool and keep the records here. The process map, fishbone, 5 Whys, driver diagram, 2×2 and the other diagrams for all 5 steps are drawn at aimqa.github.io/Test-/diagram-tool.html (pick your kit at the top). This log holds the decisions, the data and the write-up. Paste the tool’s PNGs into your slides.
– WHO quality lens: quality services are effective · safe · people-centred · timely · equitable · integrated · efficient. Your aim should target at least one.
– Count patients and do not name them: no patient-identifiable data goes in this log. If your project is research and not QI or audit, it needs Health Research Authority and research ethics committee approval before you start.
Source: WHO, Quality of care (who.int/health-topics/quality-of-care)

## Steps
Step Tracker: the 5 steps
Update the Status as you go, and Home counts the ‘Done’ rows. ‘You’re done when…’ is each step’s exit test, as in the Roadmap.
# | Step | You’re done when… | Owner | Status | Target date | Completed | Notes / link
1 | Understand the problem | The team shares one picture of the problem (where it happens, who it affects and why) with a first count, and the project type is settled (QI / audit / research) |  | Not started
2 | Define the problem and aim | A measurable aim, 3 measures, a baseline run chart and a one-page data plan, with the project registered and your supervisor’s “yes” |  | Not started
3 | Choose change ideas | A driver diagram and one change chosen from the 2×2; the team knows the plan and the start date is in the diary |  | Not started
4 | Test and measure improvement | 6 to 8 post-change data points, a project diary and a team decision: keep, tweak or drop |  | Not started
5 | Sustain, spread and share | An owner and a re-check date, all 18 SQUIRE items ticked (or justified), and the project shared |  | Not started

## Actions Log
Actions and Decisions Log: the team’s conversation in one place
Every step. Add a row here instead of sending a WhatsApp message, so anyone opening the file can see who’s doing what. Overdue open actions turn red.
Date | Type | Raised by | Detail | Owner | Due | Status | Closed
2026-01-12 | Action | A. Khan (foundation doctor) | EXAMPLE: print 50 updated clerking proformas and restock the admissions trolley | B. Patel (nurse in charge) | 2026-01-19 | Done | 2026-01-16

## Process Map
Process Map: what actually happens, step by step
Step 1: Understand the problem. Walk the route with the people who do the work and map what really happens, which may not match the policy. Flag where it goes wrong: those steps become your change ideas.
# | What happens (one line) | Who does it | Typical time (mins) | Waiting before this step (mins) | Problem here? | What goes wrong | Idea to fix it → driver diagram | AT A GLANCE (updates itself)
e.g. | Drug chart written | Admitting doctor | 10 | 45 | Yes | Chart waits ~45 min for a free doctor; VTE section then skipped when the take is busy | Prompt line on the clerking proforma | Steps mapped | 0
[8 empty] | Steps flagged as a problem | 0
[8 empty] | Hands-on time, end to end (mins) | 0
[8 empty] | Waiting time, end to end (mins) | 0
Share of the journey spent waiting
A long wait next to a short task is usually where the delay is, and often the easiest thing to fix.
Draw it as a picture → aimqa.github.io/Test-/diagram-tool.html. The Process Map tab turns these steps into a diagram you can paste into your slides.

## Causes
Causes: what is driving the problem
Step 1: Understand the problem. Draw the fishbone in the tool, then log the causes here. The evidence column matters most, because it separates what you have actually checked from what the team only suspects.
# | Category | Cause (one line) | How do we know? (evidence, or ‘hunch’) | Evidence? | Worth tackling? | Becomes which driver? | AT A GLANCE (updates itself)
e.g. | Process | Nothing prompts VTE while the chart is written | Watched 6 clerkings; no prompt on the proforma | Checked | Yes | Secondary driver → prompt at the point of prescribing | Causes logged | 0
[7 empty] | Backed by evidence | 0
[7 empty] | Still just a hunch | 0
[7 empty] | Picked to tackle | 0
If everything is a hunch, you are guessing. Go and check 2 or 3 before you pick one to change.
Draw the fishbone → aimqa.github.io/Test-/diagram-tool.html. The Fishbone tab turns these causes straight into a driver diagram.

## Data Plan
Data Plan: one outcome, one process and one balancing measure
Step 2: Define the problem and aim. Define each measure so that 2 people would count it the same way. Small samples are fine: 10 to 20 cases per time point.
Measure | Type | Operational definition (what exactly counts?) | Data source | Who collects | How often | Target
EXAMPLE: VTE assessment completed | Process | VTE risk assessment completed within 14 h of the decision to admit, counted per 20 charts sampled | Drug charts, acute medical unit | Foundation doctor of the week | Weekly (Mon) | 90% by Mar 2027
Outcome
Process
Balancing
Need the diagrams first? Draw your process map and driver diagram at aimqa.github.io/Test-/diagram-tool.html, then paste the PNGs into your slides.

## Data Log
Data Log: feeds the run chart automatically
Step 4: Test and measure improvement (the baseline starts at Step 2). One row per week. Enter n and how many met the standard, and the % is calculated for you. Mark the week you launched with ★ INTERVENTION.
Week ending | Cases reviewed (n) | Met standard | % met (auto) | Balancing count | Intervention? | Context note (see Diary) | % met (chart) | Week (chart)
2026-01-12 | 20 | 12 | 60% | 0 |  | EXAMPLE: baseline week 1 | 60% | 12-Jan-26
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Diary
Project Diary: the qualitative data
Step 4: Test and measure improvement. Write a few lines a week about what changed around you and what people said. This explains the run chart, and it is where ideas for cycle 2 come from.
Date | What happened / what changed around us | Quote or comment (verbatim) | Tag | Logged by
2026-01-15 | EXAMPLE: ward at 110% capacity all week; 2 escalation beds open | “Nobody restocks the proforma tray at weekends” (Sister J.) | Hindered | A. Khan

## PDSA Log
PDSA Log: one row per cycle
Step 4: Test and measure improvement. Write the prediction BEFORE you launch (Plan), then complete the row as the cycle runs. Cycle 2 should be smaller than cycle 1.
Cycle | Dates (from – to) | PLAN: the change and your prediction | DO: what actually happened | STUDY: what the data showed | ACT: keep / tweak / drop | Next step
e.g. | 06 Jan – 02 Feb | VTE prompt line on every clerking proforma; predict completion rises 60% → 80% | Launched Monday; night shifts used old proformas in week 1, so the old stock was withdrawn | Rose to 75% by week 3; dipped every weekend | Tweak: weekend proforma restock added to the ward checklist | Cycle 2 from 09 Feb
1
2
3

## SQUIRE Check
SQUIRE Check: run this before you present or submit
Step 5: Sustain, spread and share. Mark each item Yes / No / N/A, and if N/A, justify it in Notes. Home counts the ‘Yes’ rows. Full guidance is in the SQUIRE 2.0 Reporting Guide.
# | SQUIRE item | Covered? | Where (slide / section) | Notes / justification
1 | Title: signals an improvement initiative
2 | Abstract: structured and searchable
3 | Problem description: local nature and significance
4 | Available knowledge: what’s already known
5 | Rationale: framework, assumptions, mechanism
6 | Specific aims: of the project and the report
7 | Context: setting described at the outset
8 | Intervention(s): reproducible detail and team
9 | Study of the intervention: impact and causality
10 | Measures: outcome, process, balancing
11 | Analysis: quantitative and qualitative
12 | Ethical considerations: review, harms, conflicts of interest
13 | Results: evolution, data, context, surprises
14 | Summary: key findings and strengths
15 | Interpretation: meaning, comparison, costs
16 | Limitations: validity and generalisability
17 | Conclusions: usefulness, spread, next steps
18 | Funding: sources and funder role

## Share and Replicate
Share your project: replication pack
Step 5: Sustain, spread and share. The blue boxes fill themselves in from your other tabs, and you only write the 6 white ones in section C. Then File → Print → PDF (set to fit one page) and send it with the 3 images listed at the bottom.
A WHAT WE DID (fills itself in from the Home tab)
Project title | ← fill in on Home
Aim (SMART) | ← fill in on Home
Setting it ran in | ← fill in on Home
Quality domain (WHO) | ← pick on Home
Project type | ← pick on Home
B WHAT WE CHANGED, AND WHAT HAPPENED (fills itself in from the PDSA Log and Data Plan)
The change we tested | ← fill in cycle 1 on PDSA Log
What the data showed | ← fill in cycle 1 on PDSA Log
Our verdict | ← keep / tweak / drop, on PDSA Log
Outcome measure | ← fill in on Data Plan
Process measure | ← fill in on Data Plan
Balancing measure | ← fill in on Data Plan
C WHAT YOU’D NEED TO REPEAT IT SOMEWHERE ELSE (the only part you write: 6 boxes, a line or two each)
1. Before you start | Who has to say yes (ward manager, pharmacy, IT…), and anything that must already exist, such as a proforma, a form, system access or a regular meeting.
2. What it actually cost | Money spent (often £0, so say so), plus the honest time: roughly how many hours a week, and from whom.
3. What made it work here | The local conditions that mattered, such as a supportive pharmacist, a daily board round or a ward small enough to brief in one go. This tells someone whether it will work in their setting.
4. What we’d do differently | What went wrong, what we wasted time on and what we’d skip. This is often the most useful box on the page.
5. Expect to adapt | If your setting differs (electronic instead of paper charts, a bigger ward, no pharmacist), change this part.
6. Happy to be asked? | Name and contact email of someone who will answer a question about it, and confirm they’re happy to be contacted.
D SEND THIS WITH IT (3 images and this page; nothing else is needed)
Process map (PNG) | Attached? | From aimqa.github.io/Test-/diagram-tool.html: Download PNG
Driver diagram (PNG) | Attached? | Same tool, Driver Diagram tab
Run chart | Attached? | Copy the chart from the Data Log tab
Write-up (optional) | Attached? | Only if you’ve done one (SQUIRE deck or poster)
SQUIRE items covered | 0 of 18. A write-up is optional, and this page is enough to pass the project on.
Send it to: your own QI / clinical audit team, your local QI team and the ward you’re passing it to. If it worked, consider a regional meeting or BMJ Open Quality, and ask your supervisor. Never put patient-identifiable data on this page.