## Slide 1
5 STEPS · 1 CYCLE
SOCIETY FOR ACUTE MEDICINE · QUALITY IMPROVEMENT
The SAM QI Roadmap
Five steps to better care, from the first idea to a change that lasts, and round again.
Works with the SQUIRE 2.0 Presentation Template and Reporting Guide, which you use at Step 5. SQUIRE is the Standards for Quality Improvement Reporting Excellence.
Society for Acute Medicine | Quality Improvement

## Slide 2
The 5 steps at a glance
01
Understand the problem
Build the team, map it, find the causes
A shared picture
02
Define the problem and aim
An aim, 3 measures, a baseline, the pitch
A baseline run chart
03
Choose change ideas
Driver diagram, then one quick win to test
A start date
04
Test and measure improvement
Plan–Do–Study–Act (PDSA): test small, plot every week, go round again
A team decision
05
Sustain, spread and share
Hand it on, write it up, share it
An owner and a write-up
The Model for Improvement runs through all 5 steps: questions 1 and 2 at Step 2, question 3 at Step 3 and PDSA at Step 4, then round again from Step 3.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: An overview of the 5 steps: understand the problem; define the problem and aim; choose change ideas; test and measure improvement; sustain, spread and share. The right-hand column shows the output of each step, which is its exit test. The Model for Improvement runs through all 5: questions 1 and 2 are answered at Step 2 and question 3 at Step 3, and PDSA testing happens at Step 4, which loops back to Step 3 for each new cycle.

## Slide 3
STEP 1 OF 5: GROUNDWORK FOR QUESTION 1
Understand the problem
STEP 1
What to do
Build the team first: the people who do the work, someone who can say yes and a patient or carer voice
Map what actually happens with the people who do the work, and log it on the Project Log’s Process Map tab
Draw a fishbone, then use the 5 Whys on causes with evidence
Count something: 20 sets of notes or one week of data
Decide whether it is QI, audit or research, and register it with your trust’s audit or QI office
What’s enough
A sticky-note process map, a whiteboard fishbone and one honest local number.
You’re done when…
The team shares one picture of the problem (where it happens, who it affects and why) with a first count.
Draw both online → aimqa.github.io/Test-/diagram-tool.html
FEEDS SQUIRE ITEMS 3 · 4 · 7 (see the Reporting Guide for each)
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 1: understand the problem (the groundwork for Model for Improvement question 1). Build the team first: the people the change affects, someone who can say yes and a patient or carer voice. Walk the current process with the people who do the work and map it. Use a fishbone for breadth, then the 5 Whys on the causes you have evidence for. Count something simple, decide whether the project is QI, audit or research, and register it. Both diagrams can be drawn and exported in the SAM QI Diagram Tool at https://aimqa.github.io/Test-/diagram-tool.html, which has the WHO quality lens and a worked VTE example built in. This step feeds SQUIRE items 3 (Problem description), 4 (Available knowledge) and 7 (Context).

## Slide 4
STEP 1 CONTINUED: BUILD THE TEAM FIRST
Who needs to be on board?
STEP 1
Who does the work day-to-day?
Nurses, healthcare assistants (HCAs), pharmacists and ward clerks: the people your change actually affects. Invite one onto the team.
Whose sign-off do you need?
Ward manager, clinical lead, pharmacy, information technology (IT): name them before you launch. A missing “yes” is one of the commonest reasons a first quality improvement project (QIP) stalls.
Who might resist, and why?
It’s usually about workload. Before you start, ask what would make the change easier.
Who speaks for patients?
Even one conversation counts, as does a theme from the Patient Advice and Liaison Service (PALS) or the Friends and Family Test. Note what patients say about the problem.
A lack of buy-in is the commonest reason first QIPs stall. A 5-minute conversation in the corridor now can prevent a stalled launch later. There’s a ‘who must say yes’ line on the Project Log’s Home tab.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 1, continued: build the team. Check who the stakeholders are and how patients will be heard before anything is pitched. BMJ guidance says that without stakeholder support a QIP is likely to fail, however good the idea. There are 4 prompts: who does the work day to day (invite one of them onto the team), whose sign-off is needed, who might resist and why (usually workload), and who speaks for patients (one conversation, or a theme from PALS or the Friends and Family Test, is enough for a first project). There is a matching field on the Project Log’s Home tab.

## Slide 5
STEP 1 CONTINUED: SETTLE THIS BEFORE YOU START
QI, audit or research?
STEP 1
Quality improvement
“How do we improve how we do it here?”
Testing local changes and measuring the effect, as in this Roadmap.
Register with your trust’s clinical audit / QI team. No ethics committee needed.
Clinical audit
“Are we meeting the standard?”
Measuring current practice against an agreed standard, without testing a change.
Register with the clinical audit team. No ethics committee needed.
Research
“What should best practice be?”
Creating new, generalisable knowledge, with hypotheses, controls and publication beyond your ward.
Needs Health Research Authority (HRA) and research ethics approval BEFORE you start. Speak to the research and development office.
Rule of thumb: changing something and measuring it locally = QI. Not sure? hra-decisiontools.org.uk/research decides it in 5 clicks.
Information governance (IG), whatever the label: count patients without naming them. No patient-identifiable data in workbooks, emails or on personal devices. If you really need identifiers, use trust systems only and ask your IG team first.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 1, continued: the difference between QI, clinical audit and research (HQIP guidance). QI tests a local change: register it with the audit or QI office, and no research ethics committee (REC) review is needed. Audit measures practice against a standard: register it, and no REC review is needed. Research creates generalisable knowledge and needs Health Research Authority (HRA) and REC approval before it starts. The HRA decision tool at hra-decisiontools.org.uk/research settles borderline cases. Settling the label first avoids a common mistake for newcomers: collecting data for months and then finding that the project needed approval. Information governance applies to all 3. Keep patient-identifiable data on trust systems, count patients without naming them and involve the information governance (IG) team if identifiers are really needed.

## Slide 6
STEP 1 CONTINUED: SEE THE PROCESS BEFORE YOU CHANGE IT
Map what actually happens
STEP 1
Patient arrives on AMU
Clerked by admitting doctor
VTE section done?
Wait for the drug round
First doses given
15 min
waits 2 h
Pill start / end Box a step Diamond a decision (map the ‘no’ route too) Dashed a wait or delay AMU acute medical unit VTE venous thromboembolism
How to do it
Walk the route with the people who do the work, instead of mapping it from memory at a desk
Thirty minutes and a corridor conversation is enough
Map what actually happens, including the workarounds, even where it differs from the policy
Stop at 8 to 12 steps; more than that maps the hospital instead of the problem
What you’re looking for
The waits between steps, which are usually where the delay is
The steps where it goes wrong: those become your change ideas
Steps that 2 people describe differently, because the disagreement is a finding in itself
Anything done twice, or not at all
Log the detail on the Project Log’s Process Map tab: who does each step, how long it takes, how long people wait and what goes wrong. Then draw the picture at aimqa.github.io/Test-/diagram-tool.html
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 1, continued: process mapping. Walk the route with the people who do the work instead of reconstructing it at a desk; 30 minutes is usually enough. Map what actually happens, including workarounds, even where it differs from the policy, and stop at 8 to 12 steps. Look for the waits between steps, which are usually most of the patient’s journey (the worked example shows a 15-minute task followed by a 2-hour wait); the steps where things go wrong, which become change ideas; steps that 2 people describe differently; and anything done twice or not at all. The 4 shapes match the Diagram Tool: a pill for the start and end, a box for a step, a diamond for a decision (map the ‘no’ route too) and a dashed box for a wait. The detail goes on the Project Log’s Process Map tab, which totals hands-on time against waiting time, and the picture is drawn at aimqa.github.io/Test-/diagram-tool.html. This feeds SQUIRE item 7 (Context).

## Slide 7
STEP 1 CONTINUED: LIST EVERY POSSIBLE CAUSE
Fishbone: spread wide before you go deep
STEP 1
VTE assessment
missed at clerking
People
New doctors never shown the box
Locums do not know our proforma
Process
Nothing prompts it at the chart
No check before post-take
Equipment
Proforma predates the rule
Environment
Noisy bay, interruptions
Worst at weekends
Policies
Nobody knows the 14-hour target
Patient factors
No weight → dose left blank
Why use a fishbone as well as the 5 Whys?
The 5 Whys follows one path in depth, while the fishbone covers all of them
It stops the team fixing the first cause somebody happens to name
The empty bones are informative too: they show where nobody has looked
How to run it in 20 minutes
The problem goes in the head on the right: one sentence, no blame
Take each bone in turn: “what here could be contributing?”
Write everything down first, and discuss importance afterwards
Then pick the one or two you have evidence for, and explore those in depth
Draw it online. The Fishbone tab at aimqa.github.io/Test-/diagram-tool.html turns your causes straight into a driver diagram, and the Project Log’s Causes tab records which ones you actually have evidence for.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 1, continued: the fishbone (Ishikawa or cause-and-effect diagram). Its job is breadth: getting every possible cause out of people’s heads before the team starts debating which one matters. The 5 Whys works the other way, following a single path in depth, so the 2 complement each other. The usual order is the fishbone first, then the 5 Whys on the one or two causes you have evidence for. Six categories are offered as prompts (People, Process, Equipment, Environment, Policies, Patient factors). Teams should rename any that do not fit, and leave a bone empty instead of inventing a cause to fill it. An empty bone is a finding in itself, because it usually means nobody has looked there. Run it as a 20-minute whiteboard exercise with the people who do the work. The causes then become secondary drivers on the driver diagram, and the Diagram Tool moves them across in one click. This feeds SQUIRE items 3 (Problem description) and 7 (Context).

## Slide 8
STEP 1 CONTINUED: BEFORE YOU DRAW THE DRIVER DIAGRAM
First, ask why 5 times
STEP 1
THE PROBLEM VTE assessments get missed at clerking
↓ why?
WHY 1 Doctors skip the section when it’s busy
↓ why?
WHY 2 Nothing prompts it while the chart is being written
↓ why?
WHY 3 The clerking proforma predates the VTE requirement
↓ why?
ROOT CAUSE A gap in the process, so fix the proforma.
HOW TO DO IT
Ten minutes at the whiteboard with the team; 3 to 5 whys is typical
Keep asking until you reach something you can redesign, such as a process, a form or a step
If your final ‘why’ names a person, ask why once more
The root cause becomes a secondary driver, and its fixes become your change ideas
Draw it online → aimqa.github.io/Test-/diagram-tool.html. The Diagram Tool has a 5 Whys tab under Step 1, with the process map and fishbone.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 1, continued: a simple 5 Whys before the driver diagram, as recommended for beginners by the BMJ getting-started guide, the Royal College of Surgeons of England (RCS England) trainee guide, the Royal College of Physicians and the Institute for Healthcare Improvement (IHI). The fishbone is the fuller alternative. The worked VTE chain runs: the problem → skipped when busy → no prompt at the point of writing → the proforma predates the requirement → the root cause is a gap in the process. The teaching points are to stop at a system cause you can redesign, to look at the process instead of blaming people and to carry the root cause onto the driver diagram as a secondary driver. The Diagram Tool at aimqa.github.io/Test-/diagram-tool.html includes a 5 Whys builder.

## Slide 9
STEP 2 OF 5: QUESTIONS 1 AND 2
Define the problem and aim
STEP 2
What to do
Write the problem in one sentence: what, where and for whom
Draft a one-line aim, from [X] to [Y] by [date], that targets a World Health Organization (WHO) quality domain (safe, timely, effective…)
Pick one outcome, one process and one balancing measure, and define each on the Project Log’s Data Plan tab
Collect 2 to 4 weeks of baseline data before changing anything, and plot it
Find a supervisor and a friend to share the work
Pitch it in 5 sentences: problem · number · aim · why it matters · the ask (worked example on a later slide)
What’s enough
Five sentences, one honest local number and a baseline of 10 to 20 cases a week.
You’re done when…
Your supervisor has said “yes, go ahead”, and you have a baseline run chart and a one-page data plan.
FEEDS SQUIRE ITEMS 6 · 10 · 12 (see the Reporting Guide for each) WHO quality domains → who.int
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 2: define the problem and aim (Model for Improvement questions 1 and 2). Write the problem in one sentence. Draft an aim that targets a WHO quality domain (who.int/health-topics/quality-of-care). Choose one outcome, one process and one balancing measure, each defined so that 2 people would count it the same way (Project Log, Data Plan tab). Collect 2 to 4 weeks of baseline data and plot it before changing anything. Find a supervisor, then pitch in 5 sentences: the problem, one honest number, the aim, why it matters and what you are asking for. Have one-line answers ready for the 4 questions the audience will ask (What is it? How does it work? Can you back it up? Can you do it?). This step feeds SQUIRE items 6 (Specific aims), 10 (Measures) and 12 (Ethical considerations, including registration).

## Slide 10
STEP 2 CONTINUED: WHAT DATA DO YOU NEED?
Two kinds of data, and you need both
STEP 2
Quantitative: the numbers
WHAT IT IS
Things you can count: rates, percentages, times, simple tallies.
e.g. % of drug charts with a VTE assessment · minutes to antibiotics · falls per week
WHY IT MATTERS
Shows whether things actually changed, plotted over time on your run chart
Convinces others, because a chart is more persuasive than an anecdote
Small counts are fine: 10 to 20 cases per time point, plotted honestly
Qualitative: the words
WHAT IT IS
What people say and experience: comments, quotes, what you observe.
e.g. a huddle comment · a free-text survey box · what you noticed on the ward round
WHY IT MATTERS
Tells you WHY the numbers moved: what helped and what got in the way
Picks up what numbers miss, such as workload, morale and unintended effects
Shapes cycle 2, because the best next change ideas come from what staff tell you
You need both. Numbers show whether it changed, and words tell you why. A run chart plus 3 staff quotes is a complete data set for a first QIP.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 2, continued: quantitative data (counts, rates and times) show whether performance changed, and are plotted over time on the run chart. Qualitative data (staff and patient comments, and observations) explain why the change happened, bring workload and unintended effects to light, and suggest change ideas for cycle 2. Both feed SQUIRE items 10 (Measures) and 11 (Analysis).

## Slide 11
STEP 2 CONTINUED: A SHORT PITCH
The 5-sentence pitch
STEP 2
1
The problem
What’s going wrong, and for which patients, as you’ve seen it on the ward.
2
The number
One honest local figure: “12 of 20 charts last week.” No literature review.
3
The aim
From [X] to [Y] by [date].
4
Why it matters
The WHO quality domain it targets, and what it means for patients.
5
The ask
A named supervisor, and a “yes, go ahead” to collect baseline data.
IN YOUR BACK POCKET
The 4 questions the room will ask:
“What is it?”
“How does it work?”
“Can you back it up?”
“Can you do it?”
Have a one-line answer ready for each, and keep it out of the pitch itself.
YOUR PITCH FEEDS FORWARD The aim starts Step 3’s driver diagram, which is where your change ideas are sorted.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 2, continued: the 5-sentence pitch (the problem, a number, the aim, why it matters and what you are asking for). It is deliberately short. BMJ guidance describes a short pitch built around the aim as a light step to win support, and it does not need a scripted speech. Use the 4 audience questions (What is it? How does it work? Can you back it up? Can you do it?) to prepare for the questions afterwards. This feeds SQUIRE items 3, 4 and 6.

## Slide 12
STEP 2 WORKED EXAMPLE: THE IDA PITCH IN 5 SENTENCES (ANONYMISED)
Five sentences, written out
STEP 2
1. Iron-deficiency anaemia (IDA) is one of our commonest same day emergency care presentations, and getting the work-up wrong risks missing a malignancy.
2. Last month, fewer than half of our IDA patients had the underlying cause investigated before discharge.
3. We aim to increase appropriate intravenous iron use by 25% and cut inappropriate transfusions by 90% within 12 months.
4. This matters for safe, effective care: fewer patients exposed to the risks of transfusion, and fewer reattending for infusions they did not need.
5. Dr [supervisor] has agreed to supervise, and we’re asking for the go-ahead to collect baseline data.
WHY IT WORKS
Opens on a risk that matters: missed malignancy
One honest local number, with no literature review
The aim has an X, a Y and a date
‘Why it matters’ names the WHO domains: safe, effective
Ends on a clear, small request: a supervisor and a go-ahead
Keep the fuller answers (delivery plan, measures, feasibility) for the questions afterwards.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 2 worked example: the department’s iron-deficiency anaemia pitch, shortened to 5 sentences and anonymised. Sentence 1 is the problem, 2 the local number, 3 the SMART aim, 4 why it matters (the WHO domains safe and effective) and 5 what they are asking for. The delivery plan, the 3 types of measure and feasibility are kept for the questions afterwards.

## Slide 13
STEP 3 OF 5: QUESTION 3
Choose change ideas
STEP 3
What to do
Sketch a driver diagram: aim → primary → secondary → change ideas (next slide)
Look for what has worked elsewhere, such as on the SAM Improvement Exchange
Sort your ideas on a 2×2 and pick ONE from the top left (high impact, low effort)
Design it small, so the right thing is the easy thing, such as a checklist, a prompt or a default
Agree who does what and from what date, and write down what you predict will happen
Tell everyone affected before you start (huddle, poster, ward meeting)
What’s enough
One change, one ward, a named start date. If it needs a committee, it’s too big for cycle 1.
You’re done when…
The team knows the plan and the start date is in the diary.
FEEDS SQUIRE ITEMS 5 · 8 (see the Reporting Guide for each)
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 3: choose change ideas (Model for Improvement question 3). Draw the driver diagram from the aim. Look at what other units have tried before inventing your own, for example on the SAM Improvement Exchange. Sort the ideas on the impact × effort 2×2 and choose the quick win (top left: high impact, low effort). Design the change on a small scale, so that the right thing becomes the easy thing. Assign roles and a start date, tell everyone affected and record a prediction. This step feeds SQUIRE items 5 (Rationale) and 8 (Intervention).

## Slide 14
STEP 3 CONTINUED: GETTING THE MIDDLE 2 COLUMNS RIGHT
Primary vs secondary drivers
STEP 3
Primary drivers: the headings of your theory
The 3 to 5 big things that must be true for the aim to happen.
Write them as conditions, such as “it’s easy to do in the moment”. “Put up a poster” is an action.
Common ones: people know what’s expected · it’s easy to do · the team sees its own data · someone owns it.
Test: if all of these were true, would we hit the aim?
Secondary drivers: the parts you can actually change
The specific parts of the system that would make one primary driver true.
Ward-level and concrete enough to influence, such as a step, a form, a conversation or a rota.
1 to 3 under each primary driver is plenty on a first project.
Test: if we changed this, would the driver to its left improve?
AIM
Increase completed VTE assessments on AMU from 60% to 90% by Mar 2027
→
PRIMARY DRIVER
It’s easy to do in the moment
→
SECONDARY DRIVER
Prompt at the point of prescribing
→
CHANGE IDEA
VTE prompt at the front of the clerking proforma
Read it left to right as one sentence: we’ll achieve the aim BECAUSE this driver changes, which will change BECAUSE of this secondary driver, which we’ll test with this change idea.
Three things that catch people out: 1. If it names a poster, checklist or proforma, it’s a change idea. 2. If nobody could disagree with it, it’s too vague to be a driver. 3. More than 5 primary drivers usually means some are really secondary drivers.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 3, continued: primary and secondary drivers. Primary drivers are the 3 to 5 big conditions that must be true for the aim to be achieved. Write them as states instead of actions, and test them by asking whether the aim would follow if all of them were true. Secondary drivers are the specific, ward-level parts of the system that would make one primary driver true; 1 to 3 under each primary driver is enough for a first project. Test each by asking whether changing it would improve the driver to its left. Change ideas name the artefact or action to test in a PDSA cycle. Common errors are change ideas written in the driver columns, drivers so bland that nobody could disagree with them and too many primary drivers. The same guidance is built into the SAM QI Diagram Tool at https://aimqa.github.io/Test-/diagram-tool.html.

## Slide 15
STEP 3 CONTINUED: CHOOSING WHAT TO TEST FIRST
Sort your ideas on a 2×2
STEP 3
IMPACT →
EFFORT →
QUICK WINS: START HERE
big bets: later cycles
park these
low effort, but low yield
IDA pathway
ePrescribing prompt
One-off high-dose approval
Education sessions
Posters
HOW TO USE IT
Sticky notes on a whiteboard, 2 minutes per idea, with the team
Ask of each: how much would it move the aim? Could WE deliver it this rotation?
No scores needed: where it sits against the others is enough
Pick ONE from the top left for cycle 1; park the rest for later cycles
These 5 are from the IDA pitch. The pathway is the clear choice: high impact, and deliverable this rotation.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 3, continued: sorting change ideas on a simple impact × effort 2×2, the prioritisation matrix for beginners recommended by NHS Quality, Service Improvement and Redesign and NHS Education for Scotland, instead of a scored table from 0 to 5. Quick wins (top left: high impact, low effort) go first. Big bets (top right) wait for later cycles. Low-effort, low-yield ideas and high-effort, low-impact ideas are parked. The layout is the same as the Diagram Tool’s 2×2 Ideas tab. The example uses the ideas from the anonymised IDA pitch, where the pathway is the quick win.

## Slide 16
STEP 4 OF 5: PDSA, PLAN AND DO
Test and measure improvement
STEP 4
What to do
Launch on the planned date, and be visible in week 1
Keep collecting the same measures, the same way, every week
Keep a project diary of tweaks made and what changed around you
Do not worry about a dip; the next slide shows what counts as a signal
Run for 6 to 8 weeks after the change
What’s enough
Same counting rules as baseline, plus a few diary lines a week.
You’re done when…
You have 6 to 8 post-change data points and a diary of what really happened.
FEEDS SQUIRE ITEMS 9 · 10b to 10c · 13a (see the Reporting Guide for each)
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 4: test and measure improvement (PDSA: Plan and Do). Launch on the planned date, keep measuring in exactly the same way, keep a diary of the context and continue for 6 to 8 weeks after the change. The next 3 slides cover Study (reading and presenting the run chart) and Act (keep, tweak or drop, then round again from Step 3). This step feeds SQUIRE items 9 (Study of the intervention), 10b to 10c (tracking the context, and data quality) and 13a (evolution of the intervention).

## Slide 17
STEP 4 CONTINUED: SIGNAL OR NOISE?
How to read your run chart
STEP 4
median
↓ change launched
astronomical point: check the diary
SHIFT: 6+ in a row above the median
(example: % of drug charts with VTE assessment completed, rising after launch)
Shift
6 or more consecutive dots on the same side of the median show a real change.
Trend
5 or more dots all rising or all falling show a drift in either direction.
Astronomical point
One dot far from the rest. Check the diary for the reason, and do not change course because of it.
Mark events on the chart, but react to very few. Mark the launch, staffing changes and winter pressures on the chart, and never change course because of a single dot. Aim for 10 to 12 dots before drawing a conclusion.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 4, continued: the basics of reading a run chart for beginners (the IHI QI104 rules, and the appendix of the RCS England trainee guide). A shift is 6 or more consecutive points on one side of the median. A trend is 5 or more consecutive points all increasing or all decreasing. An astronomical point is a single data point far from the rest; look for the reason in the project diary instead of reacting to it. Mark the launch date and events in the context on the chart, do not react to single points and expect to need about 10 to 12 points before drawing conclusions. Full SPC is not covered here, because control charts are not needed for a first project.

## Slide 18
STEP 4 CONTINUED: STUDY
Present your data
STEP 4
What to do
Plot the baseline and post-change data on ONE run chart, with an arrow at the change
Add the headline: before vs after, against your aim
Say what surprised you, what helped, what got in the way
Present for 10 minutes at the QI or governance meeting
Ask the room: keep, tweak or drop the change?
What’s enough
One Excel run chart and 3 messages, told honestly.
You’re done when…
The team has seen the chart and agreed what happens next.
FEEDS SQUIRE ITEMS 11 · 13 (see the Reporting Guide for each)
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 4, continued (Study): one combined run chart, the headline result, surprises and context, a 10-minute presentation and a team decision. This feeds SQUIRE items 11 (Analysis) and 13 (Results).

## Slide 19
STEP 4 CONTINUED: ACT, THEN ROUND AGAIN
Repeat the cycle
STEP 4
What to do
Ask: what would we change after cycle 1?
Adjust the intervention, or try the next driver
Go round again from Step 3; the planning is already done
Rotating on? Hand over the data plan, diary and run chart
Working? Step 5 makes it last and spreads it
What’s enough
Cycle 2 is smaller than cycle 1, because you are refining the change. One page is enough to pass it on.
You’re done when…
The next cycle has an owner and a start date, even if the owner is not you.
FEEDS SQUIRE ITEMS 13 (how the change evolved, cycle by cycle)
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 4, continued (Act): learn from cycle 1, adjust and go back to Step 3 for the next cycle, which should be smaller and more focused. If you are rotating, hand the project over properly. When the change is working, Step 5 makes it part of everyday work and spreads it. This feeds SQUIRE item 13 (Results, including how the intervention evolved).

## Slide 20
STEP 5 OF 5: IMPLEMENT AND SPREAD
Sustain, spread and share
STEP 5
What to do
Build the change into everyday work, such as the proforma, the checklist or the induction pack
Name an owner for after you rotate, and a date to re-check the run chart
Hand over the next cycle: data plan, diary and run chart, to a named person
Write it up to SQUIRE (next slide), with a 300-word abstract if it goes to the SAM conference
If you choose, share it on the SAM Improvement Exchange for the next unit
Fill in the Project Log’s Share and Replicate tab: one page, mostly filled in for you
What’s enough
One owner, one re-check date and one page to pass it on. Sustaining a change depends on a named person and a date.
You’re done when…
The change has an owner and a re-check date, the write-up is done, and it has been shared.
FEEDS SQUIRE ITEMS 14 to 17 (then 1 and 2, written last)
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 5: sustain, spread and share (the IHI’s guidance on implementing and spreading changes). Build the change into standard work so that it does not depend on one person. Name an owner and a re-check date, hand over the next cycle and write the project up to SQUIRE with the Reporting Guide. If it goes to the SAM conference, the QI abstract checker helps you fit a 300-word abstract to SAM’s format, and, if you choose, you can share it on the SAM Improvement Exchange. The Project Log’s Share and Replicate tab is the one-page pack, and sections A, B and D fill themselves in from Home, the PDSA Log, the Data Plan and the SQUIRE Check. This step feeds SQUIRE items 14 to 17 (Summary, Interpretation, Limitations and Conclusions, including sustainability and spread), then 1 and 2.

## Slide 21
STEP 5 CONTINUED: WRITE IT UP
The SQUIRE write-up
STEP 5
What to do
Start with the Reporting Guide, which says “what’s enough” for each of the 18 items
Want fill-in slides? The Presentation Template is optional, so use only the slides you need
Write the title and abstract last
Run the 18-item self-check on the final slide
Share it somewhere, such as a local QI day, a regional meeting, a poster or the Exchange
What’s enough
A few honest sentences per item. SQUIRE itself says to skip what does not apply, and say why.
You’re done when…
All 18 items ticked (or justified), and the write-up shared.
FEEDS SQUIRE ITEMS 1 to 18 (all covered in the Reporting Guide)
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Step 5, continued (the write-up): work through the Reporting Guide, which says what is enough for each item. The fill-in Presentation Template is an optional aid, and the authors of SQUIRE 2.0 advise leaving out items that do not apply, with a reason. Write the title and abstract last, run the 18-item self-check, then submit. This covers SQUIRE items 1 to 18.

## Slide 22
OPTIONAL EXTRA: FOR WHEN YOU PRESENT YOUR WORK (STEPS 4 AND 5)
Bringing a presentation to life
OPTIONAL
The pitch itself stays at 5 plain sentences. When you present the finished work, 3 storytelling techniques make a talk more engaging:
The opening: your reason for being
One or two sentences on the moment this problem started to matter to you: your ‘aha’ moment.
“The third time I watched a patient reattend for an infusion they didn’t need, I started counting.”
The callback
Later in the talk, return to that opening with a short anecdote that confirms it.
“Remember that third patient? She’s why the pathway carries a reattendance measure.”
The ‘all is lost’ moment
Name the problem that nearly stopped the project, or still threatens it, then say how you’ll overcome it.
“Pharmacy sign-off stalled for a month, so we took it to the joint medicines committee.”
Save these for Steps 4 and 5. The room still decides on “What is it?” and “How does it work?”. The storytelling helps people remember the answers.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: Optional appendix on storytelling when you present (kept out of the Step 2 pitch, in line with the BMJ and RCS England guidance for beginners), taken from the acute internal medicine (AIM) pitch guidance. (1) The opening, or reason for being: one or two sentences on the ‘aha’ moment that got you involved. (2) The callback: return to the opening later with an anecdote that confirms it. (3) The ‘all is lost’ moment: the problem that threatened (or still threatens) the project, and how you overcame it or plan to. About 25 sentences in a logical order make a workable 3-minute pitch. The first 2 questions (What is it? How does it work?) matter most and deserve the most attention. The quotes are fictional examples in the style of the IDA worked example.

## Slide 23
A REALISTIC TIMETABLE: STRETCH OR SHRINK IT TO FIT
Fits a 4-month rotation
1
Understand
Weeks 1 to 2
2
Define and baseline
Weeks 3 to 6
3
Choose the change
Week 7
4
Test and measure
Weeks 8 to 13
5
Sustain and share
Weeks 14 to 16
The numbers are the steps. Step 4 loops back to Step 3 for the next cycle, and Step 5 is the handover and the write-up.
Rotating on before it’s finished?
Step 5 becomes a handover: pass on the data plan, the diary and the run chart to a named person. A QIP handed over like that counts as finished work.
Most first QIPs fit one rotation, and cycle 2 often belongs to the next trainee.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap
Notes: A suggested pace across a 4-month rotation: understand the problem (weeks 1 to 2), define the aim and collect the baseline (3 to 6), choose the change (7), test and measure (8 to 13), and sustain, write up and share (14 to 16). There is handover guidance for trainees who rotate on before the end.

## Slide 24
Start this week.
1
Find a problem that bothers you
2
Count something (20 sets of notes is enough)
3
Book a slot to pitch it at the next QI meeting
Every finished QIP started here, at Step 1. If you have questions, speak to your local QI team.
Society for Acute Medicine | Quality Improvement
SAM QI Roadmap