SMART Aim Statement Builder

Turn a vague problem into a SMART aim (specific, measurable, achievable, relevant and time-bound) before you collect baseline data.

THE PATTERN

To  [increase / reduce]  [measure]  from  [X]  to  [Y]  by  [date].

Worked example: “Increase venous thromboembolism (VTE) risk assessments completed within 14 hours of the decision to admit on the acute medical unit from 60% to 90% by March 2027, measured by weekly checks of 20 drug charts.”

YOUR AIM: FILL IN THE BLANKS

| INCREASE / REDUCE | MEASURE (WHAT, WHERE) | FROM (X) | TO (Y) | BY (DATE) |
| --- | --- | --- | --- | --- |

MEASURED BY

How, and how often, will you check progress? (e.g. weekly spot-check of 10 to 20 charts, a fixed audit day each month)

YOUR AIM IN ONE SENTENCE

The blanks above, written out as the sentence you will say when you pitch.

SELF-CHECK BEFORE YOU PITCH

| ☐ | S Specific | Names one measure and one place. “Improve VTE care” is too vague. |
| --- | --- | --- |
| ☐ | M Measurable | A number goes in and a number comes out, with no judgement calls. |
| ☐ | A Achievable | Stretching, but possible in the time you have. For a first project, that means one ward and one change. |
| ☐ | R Relevant | Linked to a problem your team actually notices day to day. |
| ☐ | T Time-bound | A real date, one you’ll still be around for or can hand over cleanly. |